## Summary
Eclat — V1 Backend Story Point Plan
Aligned to quotation ECL-V1-2026-001 · 30 storefront/admin screens · P1 scope only (Discounts, QR certificate, Blog, Watch&Shop, Loyalty, Gift cards, Bundles, Configurator are V2)
Track | Tickets | Total Story Points | Suggested Weeks | Notes
Foundation & Shared Platform | 19 |  | W2 – W3 | Blocks both tracks: schema, auth infra, integrations, stock engine, webhooks
Storefront Backend (/v1/*) | 31 |  | W3 – W5 | Customer-facing API consumed by eclat-web
Admin Backend (/admin/v1/*) | 33 |  | W3 – W6 | Staff/Owner-facing API consumed by eclat-admin
TOTAL
Build sequence (backend only, weeks map to §14/§Timeline W2–W6):
• W2 — Foundation: project setup, full Prisma schema + migrations + seed, cross-cutting middleware (errors, Redis, rate limits), stock engine.
• W3 — Foundation integrations (Razorpay/Shiprocket/WhatsApp/webhooks/queues) finish; Storefront identity+catalogue; Admin access+catalogue mgmt begin in parallel.
• W4 — Storefront cart/checkout/order-lifecycle; Admin catalogue mgmt completes, orders & fulfillment begin.
• W5 — Storefront post-purchase/content/marketing; Admin deliveries, customers, reviews, content, dashboard.
• W6 — Admin reports & settings finish; end-to-end test & content load, 50-concurrent-checkout stock test, backup/restore drill.
• W7 — Launch. No new backend tickets; bug-fix buffer only.

## 0. Foundation & Shared Platform
0. Foundation & Shared Platform
Seq | Ticket ID | Phase | Title | Description | Story Points | Week | Depends On
1 | F-01 | 0. Setup | Repo & project conventions | Express+TS project structure (Modules pattern: controller/dto/repository/service), ESLint/Prettier, env config, npm scripts, README | 3 | W2 | -
2 | F-02 | 0. Setup | CI pipeline | Lint + typecheck + test on PR; staging deploy workflow | 5 | W2 | F-01
3 | F-03 | 1. Data model | Prisma schema — identity & catalogue | Customer, Address, Category, Product, ProductImage, OptionType, Variant, Inventory, InventoryMovement models + migration | 8 | W2 | F-01
4 | F-04 | 1. Data model | Prisma schema — commerce | Cart, CartItem, Order, OrderItem, Payment, Refund, Shipment, ShipmentEvent, Return models + migration | 8 | W2 | F-03
5 | F-05 | 1. Data model | Prisma schema — content, ops & support | Review, Collection, Tag, Content, Page, FAQ, NotificationTemplate, Notification, AdminUser, AuditLog, Settings, Pincode, WebhookEvent, StockAlert models + migration | 8 | W2 | F-03
6 | F-06 | 1. Data model | Seed script & default settings | Seed 4 categories, sample products, India pincode dataset, and default Settings row (COD limit, free-shipping threshold, returns window) so store can read sane defaults before Admin Settings UI exists | 5 | W2 | F-04, F-05
7 | F-07 | 2. Cross-cutting | Error envelope & Zod validation middleware | Standard `{code,message,details}` error shape; stable error codes (OUT_OF_STOCK, PINCODE_NOT_SERVICEABLE, COD_NOT_ALLOWED, ...); Zod request validation | 3 | W2 | F-01
8 | F-08 | 2. Cross-cutting | Redis connection & session/cache layer | Redis client for sessions, cart cache, rate-limit counters | 3 | W2 | F-01
9 | F-09 | 2. Cross-cutting | Rate limiting middleware | Redis-backed limits: OTP 5/10min per phone, login 10/15min per IP, checkout 20/min per session | 3 | W2 | F-08
10 | F-10 | 2. Cross-cutting | Idempotency-Key middleware | Honour Idempotency-Key header on checkout and admin refund/ship POST routes | 3 | W3 | F-07
11 | F-11 | 2. Cross-cutting | Audit log middleware | Every mutating admin call writes an audit_log row (who/what/diff) | 3 | W3 | F-05
12 | F-12 | 3. Stock engine | Stock reserve/commit/release functions | Transactional reserve_stock / commit_stock / release_stock — only these three mutate stock; DB constraint reserved<=on_hand; writes inventory_movements | 8 | W3 | F-03
13 | F-13 | 4. Media | S3 + CloudFront media service | Upload endpoint, resize pipeline (200/600/1200/2000), WebP/AVIF output | 5 | W3 | F-01
14 | F-14 | 5. Integrations | Razorpay client wrapper | Create order, verify checkout signature, refund API, webhook signature verify | 5 | W3 | F-07
15 | F-15 | 5. Integrations | Shiprocket client wrapper | Auth token refresh, serviceability check, create order/AWB, fetch label+manifest, tracking fetch | 8 | W3 | F-07
16 | F-16 | 5. Integrations | WhatsApp / SMS / Email notification clients | WhatsApp Business API template sender, SMS fallback (MSG91/Twilio), Email (Resend/SES) — single NotificationService interface | 8 | W3 | F-07
17 | F-17 | 6. Async & webhooks | Webhook ingestion framework | Generic signature-verified webhook receiver; `webhook_events(provider,event_id)` unique table for idempotent processing | 5 | W3 | F-05
18 | F-18 | 6. Async & webhooks | BullMQ queue & worker process | Worker process for notification sends, webhook-retry, checkout/COD timeouts, stock release | 5 | W3 | F-08
19 | F-19 | 7. Search | Postgres full-text search | search_tsv column + GIN index + trigram index on product name for typo tolerance, updated by trigger on product save | 3 | W3 | F-03
TOTAL STORY POINTS

## 1. Storefront Backend
1. Storefront Backend
Seq | Ticket ID | Phase | Title | Description | Story Points | Week | Depends On
1 | S-01 | 1. Identity | Customer OTP auth | POST /v1/auth/otp/send, /verify — phone OTP, issues JWT (15min access + refresh cookie) | 5 | W3 | F-09, F-16
2 | S-02 | 1. Identity | Guest session & cart/wishlist merge | x-session-id guest sessions; merge guest cart+wishlist into account on login | 5 | W3 | S-01
3 | S-03 | 1. Identity | Profile & addresses | GET/PUT /v1/me; /v1/me/addresses CRUD with pincode -> city/state autofill; prefill last address for returning customers | 5 | W3 | S-01, F-06
4 | S-04 | 2. Catalogue | Categories endpoint | GET /v1/catalogue/categories (4 categories, banner, position) | 3 | W3 | F-03
5 | S-05 | 2. Catalogue | Products list (filters + sort) | GET /v1/catalogue/products — category, price range, grade, metal, size, rating, in-stock, occasion/tag filters; sort; pagination 24/page | 8 | W3 | F-03, F-19
6 | S-06 | 2. Catalogue | Product detail | GET /v1/catalogue/products/:slug — variants, images, Pearl Passport fields, material badges, related products; hide rating until >=1 approved review | 5 | W3 | S-05
7 | S-07 | 2. Catalogue | Collections & mega menu resolver | GET /v1/catalogue/collections/:slug (manual order or auto-rule: tag/price/new/rating); menu-group listing for mega menu | 8 | W4 | F-03, F-05
8 | S-08 | 2. Catalogue | Search endpoint | GET /v1/catalogue/search — instant (2+ chars) and full results, typo-tolerant | 5 | W4 | F-19
9 | S-09 | 2. Catalogue | FAQ endpoints | Global PDP FAQs + per-product FAQs | 2 | W4 | F-05
10 | S-10 | 3. Wishlist & alerts | Wishlist | GET/PUT /v1/wishlist — synced on login, localStorage for guests | 3 | W4 | S-01
11 | S-11 | 3. Wishlist & alerts | Stock-alert subscribe | POST /v1/stock-alerts — notify-me for out-of-stock variant | 2 | W4 | F-03
12 | S-12 | 4. Cart & checkout | Cart | GET/PUT /v1/cart — add/update/remove items, gift-wrap toggle + message (150 chars) | 5 | W4 | F-03
13 | S-13 | 4. Cart & checkout | Pincode serviceability | GET /v1/shipping/pincode/:pin?cod=1 — ETA + COD eligibility via Shiprocket (cached) | 5 | W4 | F-15
14 | S-14 | 4. Cart & checkout | Checkout start (prepaid) | POST /v1/checkout/start — validate cart, serviceability, reserve_stock, create Order (pending_payment) + Razorpay order | 8 | W4 | F-12, F-14, S-12, S-13
15 | S-15 | 4. Cart & checkout | Checkout verify (prepaid) | POST /v1/checkout/verify — Razorpay signature verify, mark payment captured only after verification | 5 | W4 | S-14
16 | S-16 | 4. Cart & checkout | COD checkout path | cod_unconfirmed status, cod_confirm_deadline from Settings (F-06); eligibility = pincode COD-serviceable AND total<=COD max AND no excluded item | 5 | W4 | S-14, F-06
17 | S-17 | 5. Order lifecycle | Payment webhook handling | /hooks/razorpay — payment.captured/failed/refund.processed -> commit_stock or release_stock, order_events | 8 | W4 | F-14, F-17, F-12
18 | S-18 | 5. Order lifecycle | WhatsApp COD-confirm webhook | /hooks/whatsapp — Yes/No button reply -> commit_stock (confirmed) or release_stock (cancelled) | 5 | W4 | F-17, S-16
19 | S-19 | 5. Order lifecycle | Checkout & COD timeout workers | 15-min payment timeout and COD confirm-deadline workers -> release_stock + cancel (reason logged) | 5 | W4 | F-18, S-14, S-16
20 | S-20 | 5. Order lifecycle | Order confirmation notification | Trigger order_confirmed WhatsApp (SMS fallback if undelivered in 10 min) | 3 | W4 | F-16, S-17
21 | S-21 | 5. Order lifecycle | Orders list, detail, track | GET /v1/orders, /v1/orders/:number, /v1/orders/track (order id + phone, no login) | 5 | W4 | S-01
22 | S-22 | 5. Order lifecycle | Live tracking from Shiprocket | Shiprocket tracking webhook -> shipment_events -> map to out_for_delivery/delivered/undelivered/rto_*; 2h polling fallback | 5 | W5 | F-15, F-17, F-18
23 | S-23 | 5. Order lifecycle | Shipped/delivered notification triggers | shipped (AWB+link), out_for_delivery, delivered, return_update WhatsApp templates | 5 | W5 | F-16, S-22
24 | S-24 | 6. Post-purchase | Cancellation | POST /v1/orders/:number/cancel — allowed until cancel_allowed_until (placed+24h or pre-ship); auto-refund if prepaid | 5 | W5 | S-21, F-14
25 | S-25 | 6. Post-purchase | Returns request | POST /v1/orders/:number/return — reason + photos, unboxing video required for damage claims, window/category exclusion rules from Settings | 5 | W5 | S-21, F-06
26 | S-26 | 6. Post-purchase | Reviews submit & list | POST /v1/reviews (delivered-order + not-already-reviewed only); GET reviews by product | 5 | W5 | S-21
27 | S-27 | 6. Post-purchase | All-reviews page | GET /v1/reviews — filter by rating, photo strip, summary bars | 3 | W5 | S-26
28 | S-28 | 7. Content & marketing | Content & pages endpoints | Home sections (hero, trust row, harvest picks, budget tiles, banners, farm story, comparison table, Instagram grid), CMS pages (About/FAQ/Privacy/T&C/Returns/Shipping/Size guide), announcement bar | 5 | W5 | F-05
29 | S-29 | 7. Content & marketing | Welcome popup + consent capture | Popup config read; POST subscribe with WhatsApp/SMS/email consent + timestamp | 3 | W5 | F-05
30 | S-30 | 7. Content & marketing | Analytics & feed hooks | Server-side purchase event (GA4/Meta CAPI); GET /feeds/google.xml product feed | 5 | W5 | S-21
31 | S-31 | 7. Content & marketing | Guest-to-account conversion | One-tap account creation on success page using already-verified phone | 2 | W5 | S-01, S-21
TOTAL STORY POINTS

## 2. Admin Backend
2. Admin Backend
Seq | Ticket ID | Phase | Title | Description | Story Points | Week | Depends On
1 | A-01 | 1. Access | Admin auth (email+password+2FA) | POST /admin/v1/auth/login + TOTP verify; httpOnly session cookie + CSRF token | 5 | W3 | F-09
2 | A-02 | 1. Access | RBAC middleware | Owner vs Staff role guard on every admin route; strip revenue fields server-side for Staff (dashboard, reports) | 5 | W3 | A-01
3 | A-03 | 1. Access | Staff management & audit log viewer | Invite by email, assign role, deactivate; GET /admin/v1/audit | 5 | W3 | A-02, F-11
4 | A-04 | 2. Catalogue mgmt | Categories CRUD | Name/slug/image/banner/description/position/status; product assignment & drag order | 5 | W3 | A-02, F-03
5 | A-05 | 2. Catalogue mgmt | Products list & search | GET /admin/v1/products — image, category, variant count, price range, stock, status, rating filters | 3 | W3 | A-02, F-03
6 | A-06 | 2. Catalogue mgmt | Product create/edit — basics & pearl details | Name, category, subtitle, description, tags, status; pearl type/grade/size/colour/lustre/pond/harvest batch/time-in-water/setting/purity | 5 | W4 | A-05
7 | A-07 | 2. Catalogue mgmt | Product variants | Option types (e.g. Size), generate combinations, per-variant SKU/price/MRP/stock/weight/barcode/image | 8 | W4 | A-06, F-12
8 | A-08 | 2. Catalogue mgmt | Product media | Drag-drop image upload/reorder/alt text, video URL | 5 | W4 | A-06, F-13
9 | A-09 | 2. Catalogue mgmt | Product SEO, visibility & duplicate | Slug/title/meta/OG image; featured/new-harvest/related products; duplicate product | 3 | W4 | A-06
10 | A-10 | 2. Catalogue mgmt | Product CSV import/export & bulk edit | Import/export using client product-sheet template; bulk price/stock edit | 5 | W4 | A-07
11 | A-11 | 2. Catalogue mgmt | Collections & Tags admin | Manual/auto-rule collections, menu-group + position (drives mega menu); tag kinds (occasion/pearl_type/colour/recipient) + bulk assignment | 8 | W4 | A-02, F-05
12 | A-12 | 3. Inventory | Inventory management | Stock by SKU (on_hand/reserved/available), low-stock threshold, adjustments with reason, movement history log | 5 | W4 | A-02, F-12
13 | A-13 | 3. Inventory | Notify-me subscriptions (admin view) | List of stock-alert subscriptions per SKU | 2 | W4 | A-12, S-11
14 | A-14 | 4. Orders & fulfillment | Orders list | GET /admin/v1/orders — status/payment/date/pincode/state/order#/phone/name/AWB filters | 5 | W4 | A-02, F-04
15 | A-15 | 4. Orders & fulfillment | Order detail | Customer+addresses (editable pre-ship), items with SKU/price, totals, payment details, COD confirmation status, timeline, internal notes, activity log | 5 | W4 | A-14
16 | A-16 | 4. Orders & fulfillment | Order actions — confirm/pack/cancel/address/deliver | Confirm, mark packed, cancel (reason, auto-refund if paid), edit address pre-ship, mark delivered override | 8 | W4 | A-15, F-12
17 | A-17 | 4. Orders & fulfillment | Create shipment (Shiprocket) | Pick courier, print label, manifest -> shipments row, order -> shipped, shipped notification | 8 | W5 | A-16, F-15
18 | A-18 | 4. Orders & fulfillment | Refund action | Prepaid via Razorpay refund API; COD via manual bank transfer + UTR; Staff limited to threshold, Owner unlimited | 5 | W5 | A-16, F-14
19 | A-19 | 4. Orders & fulfillment | Bulk order actions | Bulk confirm, create shipments, print labels, export | 5 | W5 | A-17
20 | A-20 | 4. Orders & fulfillment | Resend notification action | Manual resend WhatsApp/SMS for an order from admin | 2 | W5 | A-15, F-16
21 | A-21 | 5. Deliveries | Deliveries list & tracking detail | All shipments — AWB, courier, status, last scan, EDD, exceptions; click-through tracking timeline | 5 | W5 | A-17
22 | A-22 | 5. Deliveries | RTO handling | Mark received back, restock (inventory_movement), trigger refund flow | 5 | W5 | A-21, F-12
23 | A-23 | 5. Deliveries | Returns/exchange admin flow | Approve/reject, reverse pickup via Shiprocket, return_received -> restock -> refund | 5 | W5 | A-22, S-25
24 | A-24 | 6. Customers & reviews | Customers list & detail | Profile, addresses, orders, reviews, wishlist, notes, WhatsApp opt-in, tags, "Message on WhatsApp" | 5 | W5 | A-02, F-03
25 | A-25 | 6. Customers & reviews | Customers export & GDPR delete/anonymise | CSV export; delete/anonymise on request | 5 | W5 | A-24
26 | A-26 | 6. Customers & reviews | Reviews moderation | Pending/approved/rejected queue; approve/reject/reply; rating_avg/count recalculation trigger | 5 | W5 | A-02, S-26
27 | A-27 | 7. Content & ops | Content admin — home & merchandising | Announcement messages; home section enable/order; hero slides; category circles; harvest picks (manual/auto); budget tiles; banners; farm story; comparison table; Instagram grid | 5 | W5 | A-02, F-05
28 | A-28 | 7. Content & ops | Content admin — pages & size guide | Rich-text pages editor (About/Contact/FAQ/Privacy/T&C/Returns/Shipping); size guide content | 3 | W5 | A-27
29 | A-29 | 7. Content & ops | FAQs admin | Global/shipping/returns/PDP-default/per-product FAQ management | 3 | W5 | A-27
30 | A-30 | 7. Content & ops | Welcome popup admin | Enable/delay/text/consent copy; subscriber list export | 3 | W5 | A-27, S-29
31 | A-31 | 8. Insight & config | Dashboard KPIs | Today/7d/30d selector; orders/revenue/AOV/pending-to-ship/COD-pending/returns-open; needs-attention list; 14-day sales chart; top 5 products | 8 | W5 | A-14, A-24
32 | A-32 | 8. Insight & config | Reports (Owner only) | Sales by day/week/month, by category/product, payment mix, COD vs prepaid, returns rate, top customers, abandoned carts; export | 8 | W6 | A-31
33 | A-33 | 8. Insight & config | Settings | Store info; shipping rules & thresholds; COD rules; Razorpay keys & EMI toggle; notification templates/toggles; returns window & exclusions; tax/GST rate per category; staff | 8 | W6 | A-02, F-06
TOTAL STORY POINTS